## Pre-Production Summary
Project Name
Total Estimated Assets & Implementation Times | (See other sheets for breakdowns)
Total Model Time: | 675.5
Total Rigging and Animation Time: | 5.8
Total Scripting Time: | 25.1
Total VFX Time: | 22.4
Total SFX Time: | 26.6
Total UI Time: | 21.7
Total Time: | 777.1
Scale
Unit Size:
Notes:
Unknowns

## Models
Models | Category | Model Time | UV Map Time | Texture Time | LightingTime | Approval/Adjustment Time | Total Time For Model
Low-Res Models
Main Body | Small | 7 |  |  |  |  | 17
Lens | Small | 14.5 |  |  |  |  | 14.5
Top Slant Piece | Small | 38 |  |  |  |  | 38 | Part of this time was due to trying to orient and understand the images better. It looks different from different angles
Top Mount | Small | 8 |  |  |  |  | 8
[6 empty] | Total Low-Res Model Time: | 77.5
Medium-Res Models
Lens | Medium | 44 |  |  |  |  | 40
Main Body |  | 15 |  |  |  |  | 0
Lens Mount |  | 82 |  |  |  |  | 0
BackLatch |  | 7 |  |  |  |  | 0
BackHinge |  | 4 |  |  |  |  | 0
Nameplate Mount |  | 37 |  |  |  |  | 0
Top |  | 164 |  |  |  |  | 0
Nameplate |  | 14 |  |  |  |  | 0
Lens Glass |  | 9 |  |  |  |  | 0
Top Mount |  | 55 |  |  |  |  | 0
Dial Clip |  | 45 |  |  |  |  | 0
Washer Ring |  | 32 |  |  |  |  | 0
Meter |  | 11 |  |  |  |  | 0
PushPiston |  | 28 |  |  |  |  | 0
ScrewDial |  | 48 |  |  |  |  | 0
[6 empty] | Total Medium-Res Model Time: | 40
High-Res Models
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[6 empty] | Total High-Res Model Time: | 0
1
5
1
1
1
1
90
10
15
25
8
3
30
3
10
2
15
45
[6 empty] | Total High-Res Model Time: | 266
UV Mapping
5
1
4
2
1
6
10
8
2
16
2
2
2
2
90
7
3
2
10
6
10
1
30
70
[6 empty] | Total High-Res Model Time: | 292
[6 empty] | Total Model Time: | 675.5

## Rigging and Animation
Model To Animate | Category | Rig Time | Animation Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Animation
Characters
BabaYagaHut | Large | 3 | 1 | 0.5 | 0.3 | 1 | 5.8
[6 empty] | Total Character Animation Time: | 5.8
[6 empty] | Total Rig & Animation Time: | 5.8

## Scripts
Scripts | Category | Coding Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Script
Player
PlayerMovement | Medium | 2 | 0.5 | 0.5 | 1 | 4
CameraControl | Small | 1 | 0.3 | 0.2 | 1 | 2.5
Jump | Small | 1 | 0.3 | 0.2 | 2 | 3.5
[5 empty] | Total Player Script Time: | 10
Game Events
GameReset | Small | 1 | 0.3 | 0.2 | 0.5 | 2
PlayerDeath | Small | 1 | 0.2 | 0.1 | 0.5 | 1.8
CollectItem | Medium | 2 | 0.5 | 0.5 | 1 | 4
[5 empty] | Total Events Script Time: | 7.8
Rendering
CullingObjects | Small | 1 | 0.2 | 0.2 | 1 | 2.4
TexReplacer(?) | Medium | 2 | 0.4 | 0.5 | 2 | 4.9
[5 empty] | Total Rendering Script Time: | 7.3
[5 empty] | Total Script Time: | 25.1

## VFX
VFX | Category | Art/Script Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For VFX
Camera
Shake | Medium | 0.3 | 1.5 | 0.3 | 1 | 3.1
Collect | Small | 0.3 | 1 | 0.2 | 1 | 2.5
Death | Medium | 0.3 | 1 | 0.3 | 1 | 2.6
[5 empty] | Total Camera VFX Time: | 8.2
Environmental
Fog | Large | 2 | 2 | 0.4 | 1 | 5.4
[5 empty] | Total Environmental VFX Time: | 5.4
Event
WoodCrack | Small | 1 | 1 | 0.5 | 0.5 | 3
DustPoof | Small | 1 | 1 | 0.5 | 0.5 | 3
CollectSparkle | Small | 1 | 1 | 0.3 | 0.5 | 2.8
[5 empty] | Total Event VFX Time: | 8.8
[5 empty] | Total VFX Time: | 22.4

## SFX
SFX | Category | Recording/Editing Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For SFX
Player
Damage | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Jump | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Landing | Small | 0.3 | 1 | 0.2 | 0.5 | 2
HeavyLanding | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Death | Medium | 1 | 1 | 0.2 | 1 | 3.2
[5 empty] | Total Player SFX Time: | 11.2
Environmental
BackgroundCreaks | Large | 2 | 1 | 0.5 | 1 | 4.5
BabaYagaHutStomp | Medium | 0.5 | 2 | 0.5 | 1 | 4
[5 empty] | Total Environmental SFX Time: | 8.5
Event
WoodCrack | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
DustPoof | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
CollectSparkle | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
[5 empty] | Total Event SFX Time: | 6.9
[5 empty] | Total SFX Time: | 26.6

## UI
UI | Category | Art/Scripting Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For UI
Camera
CrackScreen | Medium | 2 | 2 | 0.2 | 0.5 | 4.7
Collectable | Small | 1 | 1 | 0.2 | 0.5 | 2.7
FadeScreen | Small | 0.3 | 2 | 0.2 | 1 | 3.5
[5 empty] | Total Camera UI Time: | 10.9
Front End
TitleScreen | Large | 2 | 1 | 0.5 | 1 | 4.5
[5 empty] | Total Front End UI Time: | 4.5
Pause
PauseMenu | Large | 3 | 2 | 0.3 | 1 | 6.3
[5 empty] | Total Pause UI Time: | 6.3
[5 empty] | Total UI Time: | 21.7