## Pre-Production Summary
Project Name
Total Estimated Assets & Implementation Times | (See other sheets for breakdowns)
Total Model Time: | #REF!
Total Rigging and Animation Time: | 5.8
Total Scripting Time: | 25.1
Total VFX Time: | 22.4
Total SFX Time: | 26.6
Total UI Time: | 21.7
Total Time: | #REF!
Scale
Unit Size:
Notes:
Unknowns

## Models
Nathaniel Cook | Camera
Models | Category | Model Time | UV Map Time | Texture Time | LightingTime | Approval/Adjustment Time | Total Time For Model
Low-Res Models
Main Body | Small | 7 |  |  |  |  | 17
Lens | Small | 14.5 |  |  |  |  | 14.5
Top Slant Piece | Small | 38 |  |  |  |  | 38
Top Mount | Small | 8 |  |  |  |  | 8
[6 empty] | Total Low-Res Model Time: | 77.5
Medium-Res Models
Lens | Medium | 64 |  |  |  |  | 64
Main Body |  | 99 |  |  |  |  | 99
Lens Mount |  | 152 |  |  |  |  | 152
BackLatch |  | 19 |  |  |  |  | 19
BackHinge |  | 0 |  |  |  |  | 0
Nameplate Mount |  | 37 |  |  |  |  | 37
Top |  | 164 |  |  |  |  | 164
Nameplate |  | 14 |  |  |  |  | 14
Lens Glass |  | 9 |  |  |  |  | 9
Top Mount |  | 55 |  |  |  |  | 55
Dial Clip |  | 45 |  |  |  |  | 45
Washer Ring |  | 32 |  |  |  |  | 32
Meter |  | 11 |  |  |  |  | 11
PushPiston |  | 28 |  |  |  |  | 28
Loop Brackets |  | 35 |  |  |  |  | 35
ScrewDial |  | 48 |  |  |  |  | 48
[6 empty] | Total Medium-Res Model Time: | 812
High-Res Models
Meter Right |  | 6 | 3 | 0 | 0 |  | 9
Meter Left |  | 10 | 6 | 1 | 0 |  | 17
DialClip |  | 32 | 8 | 1 | 0 |  | 41
PushPistonBottom |  | 8 | 5 | 1 | 0 |  | 14
PushPistonTop |  | 14 | 6 | 1 | 0 |  | 21
Mport |  | 20 | 8 | 1 | 0 |  | 29
Xport |  | 0 | 6 | 1 | 0 |  | 7
LoopBracketLeft |  | 43 | 8 | 1 | 0 |  | 52
LoopBracketRight |  | 0 | 6 | 1 | 0 |  | 7
Hinge |  | 17 | 5 | 1 | 0 |  | 23
FrontClip |  | 25 | 10 | 1 | 0 |  | 36
FrontKnob |  | 40 | 12 | 5 | 0 |  | 57
CatcherPieceOuterRing |  | 12 | 8 | 1 | 0 |  | 21
CatcherPieceInnerRing |  | 12 | 6 | 1 | 0 |  | 19
Slider |  | 32 | 8 | 5 | 0 |  | 45
ScrewDialCylinder |  | 10 | 6 | 1 | 0 |  | 17
ScrewDial |  | 50 | 13 | 1 | 0 |  | 64
ScrewDialPlate |  | 110 | 10 | 1 | 0 |  | 121
TopPiece |  | 120 | 22 | 3 | 0 |  | 145
PeekholeLens |  | 5 | 3 | 1 | 0 |  | 9
Peekhole |  | 8 | 5 | 1 | 0 |  | 14
MountPiece |  | 80 | 25 | 3 | 0 |  | 108
NamePlate |  | 65 | 10 | 25 | 0 |  | 100
LensGlass |  | 5 | 3 | 1 | 0 |  | 9
LensCasing |  | 90 | 26 | 8 | 0 |  | 124
LensMount |  | 210 | 45 | 8 | 0 |  | 263
LensLock |  | 16 | 5 | 1 | 0 |  | 22
MainBody |  | 230 | 120 | 25 | 0 |  | 375
BackLatch |  | 28 | 12 | 2 | 0 |  | 42
[6 empty] | Total High-Res Model Time: | 1811
[6 empty] | Total Model Time: | 2700.5

## Rigging and Animation
Model To Animate | Category | Rig Time | Animation Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Animation
Characters
BabaYagaHut | Large | 3 | 1 | 0.5 | 0.3 | 1 | 5.8
[6 empty] | Total Character Animation Time: | 5.8
[6 empty] | Total Rig & Animation Time: | 5.8

## Scripts
Scripts | Category | Coding Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Script
Player
PlayerMovement | Medium | 2 | 0.5 | 0.5 | 1 | 4
CameraControl | Small | 1 | 0.3 | 0.2 | 1 | 2.5
Jump | Small | 1 | 0.3 | 0.2 | 2 | 3.5
[5 empty] | Total Player Script Time: | 10
Game Events
GameReset | Small | 1 | 0.3 | 0.2 | 0.5 | 2
PlayerDeath | Small | 1 | 0.2 | 0.1 | 0.5 | 1.8
CollectItem | Medium | 2 | 0.5 | 0.5 | 1 | 4
[5 empty] | Total Events Script Time: | 7.8
Rendering
CullingObjects | Small | 1 | 0.2 | 0.2 | 1 | 2.4
TexReplacer(?) | Medium | 2 | 0.4 | 0.5 | 2 | 4.9
[5 empty] | Total Rendering Script Time: | 7.3
[5 empty] | Total Script Time: | 25.1

## VFX
VFX | Category | Art/Script Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For VFX
Camera
Shake | Medium | 0.3 | 1.5 | 0.3 | 1 | 3.1
Collect | Small | 0.3 | 1 | 0.2 | 1 | 2.5
Death | Medium | 0.3 | 1 | 0.3 | 1 | 2.6
[5 empty] | Total Camera VFX Time: | 8.2
Environmental
Fog | Large | 2 | 2 | 0.4 | 1 | 5.4
[5 empty] | Total Environmental VFX Time: | 5.4
Event
WoodCrack | Small | 1 | 1 | 0.5 | 0.5 | 3
DustPoof | Small | 1 | 1 | 0.5 | 0.5 | 3
CollectSparkle | Small | 1 | 1 | 0.3 | 0.5 | 2.8
[5 empty] | Total Event VFX Time: | 8.8
[5 empty] | Total VFX Time: | 22.4

## SFX
SFX | Category | Recording/Editing Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For SFX
Player
Damage | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Jump | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Landing | Small | 0.3 | 1 | 0.2 | 0.5 | 2
HeavyLanding | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Death | Medium | 1 | 1 | 0.2 | 1 | 3.2
[5 empty] | Total Player SFX Time: | 11.2
Environmental
BackgroundCreaks | Large | 2 | 1 | 0.5 | 1 | 4.5
BabaYagaHutStomp | Medium | 0.5 | 2 | 0.5 | 1 | 4
[5 empty] | Total Environmental SFX Time: | 8.5
Event
WoodCrack | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
DustPoof | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
CollectSparkle | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
[5 empty] | Total Event SFX Time: | 6.9
[5 empty] | Total SFX Time: | 26.6

## UI
UI | Category | Art/Scripting Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For UI
Camera
CrackScreen | Medium | 2 | 2 | 0.2 | 0.5 | 4.7
Collectable | Small | 1 | 1 | 0.2 | 0.5 | 2.7
FadeScreen | Small | 0.3 | 2 | 0.2 | 1 | 3.5
[5 empty] | Total Camera UI Time: | 10.9
Front End
TitleScreen | Large | 2 | 1 | 0.5 | 1 | 4.5
[5 empty] | Total Front End UI Time: | 4.5
Pause
PauseMenu | Large | 3 | 2 | 0.3 | 1 | 6.3
[5 empty] | Total Pause UI Time: | 6.3
[5 empty] | Total UI Time: | 21.7